## Slide 1: Executive Summary
Demonstrate the business and technical value through the POV.
Validate security, connectivity, application integration, and operational readiness.
Establish a clear path from POV to Production and BAU.
POV initiation and validation.
Connector security validation.
Connector setup and configuration.
Connector and application testing.
Production deployment and transition to BAU.
POV successfully initiated and progressed through all validation stages.
Connector Security Validation completed.
Connector Setup completed.
Connector & Application Testing completed.
Production & BAU transition is currently In Progress.
Validate the solution before production rollout.
Ensure secure and reliable connector integration.
Reduce implementation and operational risks.
Accelerate transition from POV to Production.
Establish a scalable foundation for BAU operations.
Objective
Scope
Benefits
Key
Highlights
Milestones
POV Initiated
Connector Security Validation
Connector & Application Testing
Completed
Completed
Completed
In Progress
Production & BAU
Completed
Major Delay
Minor Delay
On Time
Not Initiated
Connector Setup
Completed

## Slide 2: Gemini Enterprise – Project Charter (POV Initiated → Production & BAU)
Key Milestones | Start Date | End Date | Status | Remarks
P1: POV Initiated POV initiated to demonstrate business and technical value. Objectives, scope, and success criteria defined and validated. | 10-Jan-26 | 28-Feb-26 |  | POV successfully initiated and stakeholders aligned. Environment and access readiness confirmed for validation.
P2: Connector Security Validation Security validation of required 3rd-party integration connectors. Data flows, access, and compliance controls reviewed. | 01-Mar-26 | 31-Mar-26 |  | Connector security validation completed and approved. Integration risks and controls documented.
P3: Connector Setup Setup and configuration of the approved connectors. Integration parameters and environment established. | 01-Apr-26 | 31-May-26 |  | Connector setup and configuration completed. Connectivity established across integrated applications.
P4: Connector & Application Testing Functional and integration testing across connectors and applications. Performance and operational readiness checks executed. | 01-Jun-26 | 31-Jul-26 |  | Connector and application testing completed. Results validated; ready for production transition.
P5: Production & BAU Production deployment and transition to BAU operations. Ongoing management of GE app, access, and subscriptions. | 01-Aug-26 | Ongoing |  | Production & BAU transition currently In Progress. Continuous management and optimization being established.
Completed
Major Delay
Minor Delay
On Time
Not Initiated